## stakeholder analysis
| stakeholder type |  |  |  | Stakeholder Impact
Group | Responsible | accountable | consulted | informed | outcome accountable | outcome impact | output end user | internal/external | priority (high/low/medium) | direct/indirect involvement | relationship with/interest in project | goal/success criteria | impact on project | what does the project need from this group | potential issues or concerns | management strategy/ method of communication
project sponsor | NO | NO | YES | YES | YES | YES | YES | INTERNAL | High | Direct | Project Owner | Return of investment. Project to be delivered on time within budget and to quality expectation. | High | Timely response, Informations, Mandate approval, Project funding | Specificity. Fit for purpose. User engagement. | Email
programme office | NO | YES | YES | YES | NO | YES | YES | INTERNAL | High | Indirect | Project Board, managing Project Progress. Risk and Issues management | Project to be delivered on time within budeget and to quality expectations. | High | Approval on Stages | Timely response | Slack
development teams | YES | NO | YES | NO | YES | YES | YES | INTERNAL | High | Direct | Project Developers, Quality business deliverables | Project to be delivered on time within budget and to quality expectation. | High | Enhancement of website according to the agreed requirements within agreed budget, timeline and scope | Availability | agile, Daily Stand up meetings
ARCO clinets (new & old) | NO | NO | YES | YES | NO | YES | YES | INTERNAL/EXTERNAL | Low | Indirect | User | Project outcome should be suitable for use | Low | Data provison based on current activity and interaction with basecamp | None | No communication is required
Project managers | YES | YES | YES | YES | YES | YES | YES | INTERNAL | High | Direct | Project Boards, Task Assignment and Project Resources and Completion of Task | Project to be delivered on time, within budget and to meet quality expectation. | High | Management, cordination and execution of project based on agreed scope, time and budget | Being Available. Timely response. | agile, ms teams. Email. slack. Constant collaboration
Business analysts | YES | YES | YES | YES | YES | YES | YES | INTERNAL | High | Direct | Project board. Task Assignement. Project Resources. Completion of task | Project to be delivered on time, within budget, and to meet quality expectation | High | Management, cordination and execution of tasks based on agreed scope time and budget. Planning and enhancing of product according to specification | Being available. Timely response. | agile, ms teams. Email. slack. Constant collaboration
vendors | YES | YES | YES | YES | NO | YES | NO | EXTERNAL | Low | Indirect | Project team | Project to delivered on time and to meet quality specification | Med | Data provision | Timely response | Email. Constant collaboration
PMO analysts | NO | YES | YES | YES | YES | YES | YES | INTERNAL | High | Direct | Project board. Project team Adherance of project to governance and documentation. | Project to delivered on time, budget and to meet quality specification | High | Responsible for project governance, enforcement and documentation | Being available. Timely response | agile. Email. slack. Constant collaboration
government | NO | NO | YES | NO | NO | YES | NO | EXTERNAL | High | Indirect | Product Owner | Adhearnce to policies | High | Project approval | Timely response | Email
competitors | NO | NO | NO | NO | NO | NO | YES | EXTERNAL | High | Indirect | Product Owner | Project failure | Low | Nothing | None | No communication is required
Testers | YES | YES | YES | YES | NO | YES | YES | INTERNAL | High | Direct | Project team. | Fully enhanced peoduct and test script | High | Functionability. Tested bug and defect free | Availability. Timely response. Timely delivery | Email. Constant colaboration
End Users | NO | NO | NO | YES | NO | YES | YES | INTERNAL | Low | Indirect | User | Project outcome should be suitable for use | Low | None | None | No communication is required
Executive officers | N0 | NO | YES | YES | NO | NO | NO | INTERNAL | high | direct | authorizer directors of project | Project to delivered on time and to meet quality specification | High | sign off approval and directives on the project | availability and timely response | email, slack and constant collaboration
product owner | NO | NO | YES | YES | YES | YES | NO | EXTERNAL | high | direct | product owner | Project outcome should meet the product requirement and be suitable for use | high | prduct specification, description and requirements | inadequate product information and timely respose | email, slack and MS teams
system support officers | YES | YES | NO | NO | YES | NO | NO | INTERNAL | high | direct | project team | Project to be delivered on time, within budget, and to meet quality expectation | high | Management, cordination and execution of project based on agreed scope, time and budget | Being Available. Timely response. | ms teams, slack and email

## stakeholder identification
NUMBER | STAKEHOLDER LIST | NAME
1 | project sponsor
2 | programme office
3 | development teams
4 | ARCO clinets (new & old)
5 | Project managers
6 | Business analysts
7 | vendors
8 | PMO analysts
9 | government
10 | competitors
11 | Testers
12 | End Users
13 | Executive officers
14 | product owner
15 | system support officers